## Slide 1: National Survey on Extent and Pattern of Substance Use in India
Session 7:
HHS SURVEY – KEY OPERATIONAL ASPECTS (Part 1)
National Drug Dependence Treatment Centre (NDDTC) AIIMS, New Delhi
Ministry of Social Justice & Empowerment,
Government of India
State-level Training on Household Survey
Society for Promotion of Youth & Masses, New Delhi

## Slide 2
OVERVIEW OF THE HOUSEHOLD SAMPLE SURVEY

## Slide 3: National Drug Use Survey (NDUS)
NUMBERS AND PROFILE
Household Sample Survey
Respondent Driven Sampling Survey
Focused Thematic Studies
GAPS IN SERVICE DELIVERY
Survey among Service Providers
Analysis of secondary data on treatment seekers
Components of the National Survey

## Slide 4: Household Sample Survey: Objective
National Survey
  Objective 1: To provide national and state-level estimates of proportion and absolute number of people who USE various substances and people who are suffering from SUBSTANCE USE DISORDERS in India.
Household Sample (HHS) Survey will provide the estimates for people using and dependent on Tobacco, Alcohol and Cannabis. Though information for all types of substances will be collected from respondents

## Slide 5: What is a Household Sample Survey?
A population-based epidemiological survey with a household as the primary unit of sample selection.
Requires selection of a sample of households which is representative of the population on which the survey findings are to be extrapolated.
A household survey can be of various types:
  National HHS survey (e.g. previous National Survey on Drugs)
  State-level HHS survey (e.g. NFHS)
  District-level HHS survey (e.g. DLHS)
  Sub-district level HHS survey
NDUS is a State-level HHS Survey  findings will be provided separately for each state

## Slide 6: Household Sample Survey in NDUS
State-level Household Survey in NDUS
  Adequate sample size to provide reliable estimates for a given state/UT
  All households within the state / UT should have equal probability of selection to ensure representativeness
  In NDUS, sampling has been performed in multiple stages:
    Selection of representative sample of districts
    Selection of representative sample of PSUs (villages / wards)
    Random selection of segments (rural) / CEBs (urban)
    Random selection of households (from villages / EBs)

## Slide 7: Household Sample Survey in NDUS
State
Districts
Wards / Villages
Households
Universe
Representative of the state
Representative of the district
Representative of the ward / village

## Slide 8: Household Sample Survey in NDUS
Final sample characteristics in NDUS
  Survey will be done in 186 districts of the country
  About 170 PSUs have been selected from each state / UT
  Selection of PSUs has been done in accordance with the rural/urban ratio of the state
  About 4200 households will be surveyed from each state and UT
  Interviews of about 15000 eligible individuals in each state / UT

## Slide 9: Household Sample Survey in NDUS
Before selection of households, for each selected PSU (village / EB) an updated list of households will be prepared  Mapping-Listing survey
From this updated list, 25-40 households will be selected in each PSU by random sampling
Selected households will be surveyed by field teams which will include:
  Interview of head of these households
  Interviews of all eligible individuals
Specific questionnaire for the HHS survey
  General health and lifestyle related questions from all individuals
  Detailed interview regarding substance-use behavior for all who have used any psychoactive substance within the last 1 year

## Slide 10: Household Sample Survey in NDUS
Team of two interviewers to visit each household
  One Male and One female interviewer
People will be interviewed within the households or at a safe place within the community
Number of teams per state – 13 to 18
All household interviews to be completed in about 75 days after the HHS training
Data will be collected directly on survey software by use of touch-screen tablets
Data will be revalidated by research staff of collaborating medical institutes

## Slide 11: Human Resource for Implementation
Regional Coordinator
State Coordinator
District supervisors
State Coordinator
District supervisors
RRTC
STATE/UT
DISTRICT
Field interviewers
Field interviewers
FIELD (PSU/CEB)
Regional Technical Officers / Assistants
Medical Institutes

## Slide 12: Allocation of Field Staff
S. No. | STATE | NO OF DISTRICTS | NO OF HHS DISTRICTS | NO OF RDS DISTRICTS | DISTRICT SUPERVISORS | FIELD INTERVIEWERS
1 | Andhra Pradesh | 14 | 4 | 3 | 2 | 34
2 | Arunachal Pradesh | 16 | 4 | 4 | 4 | 36
3 | Assam | 27 | 6 | 4 | 4 | 36
4 | Bihar | 38 | 8 | 5 | 4 | 30
5 | Chhattisgarh | 18 | 5 | 3 | 3 | 32
6 | Goa | 2 | 2 | 1 | 0 | 26
7 | Gujarat | 26 | 6 | 4 | 3 | 30
8 | Haryana | 21 | 5 | 4 | 3 | 30
9 | Himachal Pradesh | 12 | 3 | 3 | 2 | 34
10 | Jammu & Kashmir | 22 | 7 | 4 | 4 | 36
11 | Jharkhand | 24 | 6 | 4 | 3 | 30
12 | Karnataka | 30 | 7 | 5 | 4 | 32
13 | Kerala | 14 | 5 | 3 | 3 | 32
14 | Madhya Pradesh | 50 | 10 | 6 | 6 | 32
15 | Maharashtra | 35 | 8 | 5 | 5 | 32
16 | Manipur | 9 | 4 | 4 | 2 | 36
17 | Meghalaya | 7 | 3 | 3 | 2 | 36
18 | Mizoram | 8 | 4 | 4 | 3 | 36

## Slide 13: Allocation of Field Staff
19 | Nagaland | 11 | 5 | 4 | 3 | 36
20 | Odisha | 30 | 7 | 5 | 4 | 30
21 | Punjab | 20 | 7 | 5 | 4 | 30
22 | Rajasthan | 33 | 8 | 5 | 4 | 32
23 | Sikkim | 4 | 4 | 1 | 2 | 38
24 | Tamil Nadu | 32 | 7 | 4 | 4 | 30
25 | Tripura | 4 | 2 | 2 | 1 | 34
26 | Uttar Pradesh | 71 | 15 | 8 | 8 | 36
27 | Uttarakhand | 13 | 4 | 4 | 3 | 36
28 | West Bengal | 19 | 6 | 4 | 3 | 30
29 | Telangana | 9 | 3 | 3 | 2 | 30
A | Andaman & Nicobar | 3 | 3 | 1 | 1 | 32
B | Chandigarh | 1 | 1 | 1 | 0 | 26
C | Dadra & Nagar Haveli | 1 | 1 | 1 | 1 | 26
D | Daman and Diu | 2 | 2 | 1 | 1 | 26
E | Lakshadweep | 1 | 1 | 1 | 1 | 30
F | NCT Delhi | 9 | 9 | 1 | 1 | 28
G | Puducherry | 4 | 4 | 1 | 1 | 24
 |  | 640 | 186 | 121 | 101 | 1144
S. No. | STATE | NO OF DISTRICTS | NO OF HHS DISTRICTS | NO OF RDS DISTRICTS | DISTRICT SUPERVISORS | FIELD INTERVIEWERS

## Slide 14
BROAD STEPS IN IMPLEMENTATION OF HOUSEHOLD SAMPLE SURVEY
(At State / UT Level)

## Slide 15: HHS SURVEY: Operational Steps
Steps involved in each state/UT
State-level consultation
Support from concerned departments
Information to concerned districts
District level sensitization meetings
Support from district administration
Publicity for the survey
Initiation of HHS survey
Identification of RDS interview and multiplier sites

## Slide 16: Implementation Plan: Operational Steps
STEP 1: ENGAGING STAFF FOR HHS SURVEY
  Contract full-time field staff for 4 day training for HHS survey (District Supervisors & Interviewers) as per TORs and sanctioned numbers shared by AIIMS
  District Supervisors – about 1-2 weeks before the first training
  Field Interviewers – from the day of first training
  36 trainings, one for each state
  4 day training of HHS Field Staff (District Supervisors & Interviewers)
  Organized by ITDC with support of RCA and SIA
  Master trainers identified by RTAs to be resource persons
  Training calendar to be prepared in this workshop
HOUSEHOLD SURVEY
STEP 2: TRAINING ON MAPPING-LISTING OF PSUs
COMPLETED.

## Slide 17: Implementation Plan: Operational Steps
STEP 3: MAPPING-LISTING OF PSUs
  Field teams will map the PSUs and list the occupied households
  Also identify suitable places for interview in case household interviews are not possible
  Conduct advocacy with key stakeholders
  Distribute survey information pamphlets
  Time required
    1-2 days / PSU for a team of 2
    About 20-25 days per state
STEP 4: SELECTION OF HOUSEHOLDS
  Random sample of 25-40 households will be drawn on completion of mapping-listing operation
  Information will be automatically distributed to:
    Concerned RCA, SIA
    District Supervisors
    Field interviewers
HOUSEHOLD SURVEY
COMPLETED.

## Slide 18: Implementation Plan: Operational Steps
STEP 5: TRAINING OF FIELD TEAMS ON DATA COLLECTION
  36 trainings, one for each state
  5 day training for Field Staff (District Supervisors, Field Interviewers)
  Organized by ITDC with support of RCA and SIA
  Master trainers identified by RTAs to be resource persons
  Training calendar to be prepared in this workshop
Components
  Basics of drug use and drug use disorders
  National survey – Methodology and Operational aspects
  Interviewing skills & survey questionnaires
  Using survey software for interviews
  Ethical aspects
  Operational details of data collection for HHS
  Field visits and hands-on experience
HOUSEHOLD SURVEY
ONGOING…

## Slide 19: Implementation Plan: Operational Steps
STEP 6: DATA COLLECTION
  Teams will be deployed in selected PSUs as per the field movement plan
  List of selected households will be shared with each team
  Teams will approach selected households within each PSU and complete interviews of eligible members
  Close monitoring by district supervisors and other personnel
STEP 7: REVALIDATION
  Independent verification of data
  Representative sample of PSUs and Households from those interviewed for the survey
  Staff of the RTA will make field visits and verify the data collected
  About 30 days per state – will run in parallel with data collection
HOUSEHOLD SURVEY

## Slide 20
DATA COLLECTION FOR HOUSEHOLD SAMPLE SURVEY
(At PSU Level)

## Slide 21: Pre-requisites for HHS Survey
Completion of mapping-listing activity  Availability of Location and Layout maps and list of households for all survey PSUs
Training of field teams on HHS data collection
Preparation of field team movement plan
Preparation of PSU level plan for travel and stay of field teams
PSU-wise mapping of availability of internet connection and electricity for the hand-held devices
Letter of support from state government / local authorities
Availability of material required for HHS data collection

## Slide 22: Before proceeding for data collection
Teams should collect:
  List of PSUs assigned to various teams along with movement / travel / stay plan
  Letter of support from state government / local authorities
  List of selected households in the assigned PSUs
  Location and layout maps of the assigned PSUs
  HHS resource materials
    Hand-held devices with accessories (charging cord, etc.)
    SIM card for internet connectivity
    Power bank (if applicable)
    Memory card
    Copies of various HHS documents (questionnaire, consent forms, PIS, cover page, etc.)
    Backpack

## Slide 23: Household survey teams
Each HHS survey team will consist of:
  One male interviewer - responsible for interviewing all male members of the household between the age of 15 and 75 years
  One female interviewer - responsible for interviewing all female members of the household and children between the age of 10 and 15 years
Number of teams per PSU
  To be decided by the State Coordinator depending on operational requirements of the area.
  Usually 2-3 teams per PSU
  In areas with no internet connectivity, only one team should be deployed in any PSU.

## Slide 24: Selection of Survey Households
Selection of survey households (25-40 per PSU) will be done from the list of households prepared during mapping-listing.
The selection is performed immediately after acceptance of mapping-listing data by AIIMS and the list is stored in AIIMS server.
List of selected households can be downloaded from the AIIMS server by selecting a PSU in the Household Survey Interview option of the mobile application
  This step should preferably be performed during HHS training itself.
  This is a one-time activity. Once downloaded, the list is locally saved in the device.
The teams should prepare a hard-copy of the list so that survey work can procced even if the device is not functional / available due to any reason (HHS FORM 1).
Notes: HHS Form 1 should be discussed along with other formats on Day 5 of training (after field visit).

## Slide 25: Process of HHS Survey – PSU level
STEP 1: REACHING THE PSU
  Teams will visit the PSUs / EBs assigned to them for HHS interviews as per the field movement plan
  The location maps provided by the District Supervisor will help the teams locate the PSU
  If the team is unable to locate a PSU, it should immediately inform the District Supervisor and follow instructions
  State Implementation Agency will decide whether the travel to the PSU is to be undertaken by public transport or by private vehicle
  Teams will spend anywhere between 2-6 days in a given PSU for HHS survey
  Teams should reach the PSU latest by 9AM everyday and report to the district supervisor on phone

## Slide 26: Process of HHS Survey – PSU level
STEP 2: CONFIRMING THE PSU
  On reaching the area, the first task of the team is to verifying whether it has reached the right PSU
  For this, the teams should interact with local people and confirm whether the PSU is indeed the one where the survey work is to be performed
STEP 3: INTERACTING WITH LOCAL STAKEHOLDERS
  After confirming the PSU, the teams should meet key stakeholders of the area (identified during mapping-listing activity) and inform them about the purpose of the visit and provide an overview of the survey objectives and process
  Teams should solicit support of the local stakeholders in the survey process especially in dealing with resistance from the residents of the area

## Slide 27: Process of HHS Survey – PSU level
STEP 4: ESTABLISHING BOUDARIES OF THE PSU
  Prior to beginning interviews, teams should identify boundaries of the PSU / EB to establish a perimeter for field operations
  All boundaries of the PSU should be identified
    For e.g., if the PSU is a rectangular block, the names of three streets is not enough to unequivocally identify the PSU; all four streets bounding the PSU should be identified
  Location and layout maps will help the teams identify the PSU boundaries
  Teams should also take help of the local stakeholders in correctly identifying all boundaries of the PSU

## Slide 28: Process of HHS Survey – PSU level
STEP 5: LOCATING SELECTED HOUSEHOLDS
  With the help of local stakeholders and the layout maps, teams should locate the household selected for HHS interviews within the PSU.
  Teams will mark the structures in which selected households are located with a GREEN tick on the layout map
  If a selected household cannot be located on the map, teams should immediately inform the District Supervisor
  It may be noted that even if the household can not be located on the map, a visit to the recorded address will be necessary to consider it as Inaccessible

## Slide 29: Process of HHS Survey – PSU level
STEP 6: PLANNING DATA COLLECTION
  After locating selected households, teams should make a plan for data collection within the PSU such that the work can be completed within the time allocated for this PSU (usually 3-4 days)
  Such a plan will consist of:
    Division of work between teams
    Plan of movement within the PSU
    Deciding time and location for regrouping after completing a certain portion
  Teams should update the plan periodically depending on the progress of data collection within the PSU

## Slide 30: Process of HHS Survey – PSU level
STEP 7: CONDUCTING HHS INTERVIEWS
  Teams will now approach the selected households for survey interviews
  After completing survey interviews in one household, the team should immediately move to the next household on the list
  In some cases, the team may have to move to the next household leaving the previous household partially completed. In such cases, teams will return back to the previous household later to complete the pending work.
  Minimum of 3 visits per household are to be made to complete interviews of all members (though in many cases all interviews will be complete in 1-2 visits).

## Slide 31: Process of HHS Survey – PSU level
STEP 7: CONDUCTING HHS INTERVIEWS
  In this way, teams will move from one household to the next and collect HHS interview data.
  Teams are expected to complete interviews of 3-5 households per day.
  At this rate, 2 teams will require about 3-4 days to complete all households selected in a PSU.
  Once the teams have completed data collection from all selected households, they should inform the District Supervisor and follow instructions.
  If the field-work in a PSU completes early or is taking longer than anticipated, teams should inform the District Supervisor and follow instructions.
  The step-by-step process of data collection within a household will be discussed in next session.

## Slide 32: Process of HHS Survey – PSU level
STEP 8: REVIEW BY DISTRICT SUPERVISOR
  On completion of data collection in a PSU (as reported by field teams), the District Supervisor should conduct a desk review which will consist of:
    Review of the layout map to check if the households were correctly located.
    Review of the status of selected households on the touch-screen tablet at the completion of data collection by field teams.
    By the end of data collection, the status of all households should ideally be either completed or inaccessible.
    Number of attempts made by teams for households for various households – it is expected that at least half of the households will require multiple visits.
    Total number of eligible individuals interviewed and proportion of eligible individuals missed by the field teams (available on dashboard)
    Gender and Age distribution of the individuals interviewed (available on dashboard)
Notes: NOTE: This is a DESK REVIEW which is to be done by District Supervisors for all PSUs. This should not be confused with the ON-SITE VERIFICATION to be performed for selected PSUs (to be discussed in another session).

## Slide 33: Process of HHS Survey – PSU level
STEP 9: SUBMISSION OF HHS DATA
  Based on the review, the DS will decide whether to accept the survey data or not.
  If accepted, the DS will push the Survey Complete button on the PSU household grid screen.
  Pushing this button leads to submission of HHS data to State Coordinator and locks the PSU  no further interviews / changes possible in this PSU till State Coordinator reviews the data.
  If the DS decides to reject the data, s/he will still hit the submit button but will immediately recommend the State Coordinator to reject the submitted data so that data collection in the PSU can be repeated.

## Slide 34: Process of HHS Survey – PSU level
AFTER COMPLETION OF DATA COLLECTION IN A PSU
  Once the data has been accepted by the district supervisor, teams can move to the next PSU assigned to them.
  Teams should hand-over the location and layout maps of the PSU back to the DS at the time of desk review.
  In some instances, the DS may ask the teams to move to the next PSU immediately after completion of the data collection and plan the desk review for 2-3 PSUs together.

## Slide 35
THANK YOU…
national.survey.aiims@googlegroups.com